## Timeline
MATRIX-AI / OSA 2.0 · Delivery timeline (Phase 1 to Gate 1, Jan 31, 2027 · Phase 2 to Gate 2, Mar 31, 2027)
Default start |  | 2026-11-02 |  | Gantt start |  | 2026-10-12 |  | Blue = input. Start is typed (blue) or calculated (black): day after the latest predecessor's End, or same day as the task in 'Starts with'. End = Start + Duration − 1 (calendar days). Mark people with x. 'Waits for (resource)' = earlier task of the same person (one task at a time for each DE and BA).
[15 empty] | Functional lead | Business analyst · Sell-In, SI-SO | Business analyst · Sell-Out, Right Store, BR VR | Business analyst · Market Share, Perfect Store | Business analyst · Customer P&L, Sell-Through, BR PVC, BR EASTER | Lead architect | Data architect · WS-1, WS-2, WS-3 | Data architect · WS-4, WS-5, WS-6 | Solution architect | Data engineer · Python, WS-5 | Data engineer · Python, WS-5 | Data engineer · WS-1, WS-3 | Data engineer · WS-1, WS-3 | Data engineer · WS-2 | Data engineer · WS-2 | Data engineer · WS-4 | Data engineer · WS-6 | Data engineer · WS-6 | Data engineer · WS-2 BR | Data engineer · WS-2 SOCO | FE (role to confirm) | FE (role to confirm) | FE (role to confirm) | FE (role to confirm) | FE (role to confirm) | Oct 26 |  |  | Nov 26 |  |  |  |  | Dec 26 |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27 |  |  |  | May 27 |  |  |  |  | Jun 27 |  |  |  | Jul 27 |  |  |  | Aug 27 |  |  |  |  | Sep 27
ID | Lane | Phase | Workstream | Maturity | Phase / group | Task | Duration days | Start | End | Type | Depends on | Waits for (resource) | Other resource | Days | BA0 | BA1 | BA2 | BA3 | BA4 | DA0 | DA1 | DA2 | SA1 | DE1 | DE2 | DE3 | DE4 | DE5 | DE6 | DE7 | DE8 | DE9 | DE10 | DE11 | FE0 | FE1 | FE2 | FE3 | FE4 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27
T-01 | Mobilisation | Phase 1 |  |  |  | Blueprint workshop (4 days) | 4 | 2026-10-19 | 2026-10-22 | Task |  |  | Architect, MDLZ | 4
T-02 | Mobilisation | Phase 1 |  |  |  | Environments, travel ready |  | 2026-10-31 | 2026-10-31 | Milestone |  |  | MDLZ platform | 1 | [27 empty] | ◆
T-03 | Mobilisation | Phase 1 |  |  |  | Named team starts |  | 2026-11-02 | 2026-11-02 | Milestone |  |  | All | 1 | [28 empty] | ◆
T-04 | Dependencies | Phase 1 |  |  |  | DP&E OTC (Sell-In) domain ready |  | 2026-11-01 | 2026-11-01 | Milestone |  |  | DP&E team | 1 | [27 empty] | ◆
T-05 | Dependencies | Phase 1 |  |  |  | DP&E EPOS (Sell-Out) domain ready |  | 2026-11-01 | 2026-11-01 | Milestone |  |  | DP&E team | 1 | [27 empty] | ◆
T-06 | Dependencies | Phase 1 |  |  |  | DP&E Distributor (Sell-Out) domain ready |  | 2026-11-01 | 2026-11-01 | Milestone |  |  | DP&E team | 1 | [27 empty] | ◆
T-07 | Dependencies | Phase 1 |  |  |  | DP&E LAFPA (Customer P&L) domain ready |  | 2026-11-01 | 2026-11-01 | Milestone |  |  | DP&E team | 1 | [27 empty] | ◆
T-08 | Dependencies | Phase 1 |  |  |  | Other DP&E products (Shipments), needed by |  | 2026-11-16 | 2026-11-16 | Deadline |  |  | DP&E team | 1 | [30 empty] | ◇
T-09 | Dependencies | Phase 1 |  |  |  | Snacksync database ready for analytics, needed by |  | 2026-11-16 | 2026-11-16 | Deadline |  |  | MDLZ, Snacksync | 1 | [30 empty] | ◇
T-253 | Dependencies | Phase 1 |  |  |  | Ataccama input and process definition (KPI inventory, DQ checks), needed by |  | 2026-12-01 | 2026-12-01 | Deadline |  |  | MDLZ Data Governance | 1 | [32 empty] | ◇
T-263 | Dependencies | Phase 2 |  |  |  | Perfect Store Source accessible BR |  | 2026-11-01 | 2026-11-01 | Milestone |  |  |  | 1 | [27 empty] | ◆
T-264 | Dependencies | Phase 2 |  |  |  | Perfect Store Source accessible SOCO |  | 2026-11-01 | 2026-11-01 | Milestone |  |  |  | 1 | [27 empty] | ◆
T-265 | Dependencies | Phase 2 |  |  |  | Perfect Store Source accessible WACAM |  | 2026-11-01 | 2026-11-01 | Milestone |  |  |  | 1 | [27 empty] | ◆
T-266 | Dependencies | Phase 2 |  |  |  | Right Store Source accessible BR |  | 2026-11-01 | 2026-11-01 | Milestone |  |  |  | 1 | [27 empty] | ◆
T-267 | Dependencies | Phase 2 |  |  |  | Right Store Source accessible SOCO |  | 2026-11-01 | 2026-11-01 | Milestone |  |  |  | 1 | [27 empty] | ◆
T-268 | Dependencies | Phase 2 |  |  |  | Right Store Source accessible WACAM |  | 2026-11-01 | 2026-11-01 | Milestone |  |  |  | 1 | [27 empty] | ◆
T-269 | Dependencies | Phase 2 |  |  |  | Market share source accessible MX |  | 2026-11-01 | 2026-11-01 | Milestone |  |  |  | 1 | [27 empty] | ◆
T-270 | Dependencies | Phase 2 |  |  |  | Market share source accessible WACAM |  | 2026-11-01 | 2026-11-01 | Milestone |  |  |  | 1 | [27 empty] | ◆
T-271 | Dependencies | Phase 2 |  |  |  | Market share source accessible BR |  | 2026-11-01 | 2026-11-01 | Milestone |  |  |  | 1 | [27 empty] | ◆
T-272 | Dependencies | Phase 2 |  |  |  | Market share source accessible SOCO |  | 2026-11-01 | 2026-11-01 | Milestone |  |  |  | 1 | [27 empty] | ◆
T-279 | Dependencies | Phase 2 |  |  |  | PIF ready for ingestion |  | 2026-11-01 | 2026-11-01 | Milestone |  |  |  | 1 | [27 empty] | ◆
T-256 | Phase gates (SOW) | Shared |  |  |  | Gate 1 · Blueprint and working prototype sign-off |  | 2027-01-31 | 2027-01-31 | Milestone |  |  | MDLZ Product Lead; DP&E, Architecture, Data Governance, Business, Product | 1 | [40 empty] | ◆
T-257 | Phase gates (SOW) | Shared |  |  |  | Gate 2 · Migration complete |  | 2027-03-31 | 2027-03-31 | Milestone |  |  | MDLZ Product Lead, CDRB | 1 | [49 empty] | ◆
T-258 | Phase gates (SOW) | Shared |  |  |  | Gate 3 · User testing complete |  | 2027-06-30 | 2027-06-30 | Milestone |  |  | MDLZ Product Lead, CDRB | 1 | [62 empty] | ◆
T-259 | Phase gates (SOW) | Shared |  |  |  | Gate 4 · Integration test and UAT acceptance (go / no-go) |  | 2027-08-31 | 2027-08-31 | Milestone |  |  | MDLZ Product Lead, CDRB | 1 | [71 empty] | ◆
T-260 | Phase gates (SOW) | Shared |  |  |  | Gate 5 · Production readiness and go-live |  | 2027-10-31 | 2027-10-31 | Milestone |  |  | MDLZ Product team | 1
T-261 | Phase gates (SOW) | Shared |  |  |  | Gate 6 · Hypercare exit and transition to support |  | 2027-12-31 | 2027-12-31 | Milestone |  |  | MDLZ AMS and Product team leads | 1
T-10 | Foundations | Phase 1 |  |  | Phase 1 · Foundations | Audit design | 7 | 2026-11-02 | 2026-11-08 | Task |  |  |  | 7 | [5 empty] | x | x |  | x | [10 empty] | x
T-11 | Foundations | Phase 1 |  |  | Phase 1 · Foundations | Log design | 7 | 2026-11-23 | 2026-11-29 | Task | T-10 | T-19 |  | 7 | [5 empty] | x | x |  | x | x
T-12 | Foundations | Phase 1 |  |  | Phase 1 · Foundations | Data quality checks design | 14 | 2026-11-02 | 2026-11-15 | Task |  |  |  | 14 | [5 empty] | x |  | x | x | [6 empty] | x
T-13 | Foundations | Phase 1 |  |  | Phase 1 · Foundations | Custom tags design | 7 | 2026-11-30 | 2026-12-06 | Task | T-11 | T-241 |  | 7 | [5 empty] | x |  |  | x |  |  |  | x
T-14 | Foundations | Phase 1 |  |  | Phase 1 · Foundations | Notebook template | 14 | 2026-11-16 | 2026-11-29 | Task | T-12 |  |  | 14 | [5 empty] | x | x | x | x | [8 empty] | x
T-15 | Foundations | Phase 1 |  |  | Phase 1 · Foundations | Test dataset ZZ design | 14 | 2026-12-07 | 2026-12-20 | Task | T-13 | T-277 |  | 14 | [5 empty] | x | x | x | x |  |  | x
T-16 | Foundations | Phase 1 |  |  | Phase 1 · Foundations | Incremental load design | 7 | 2026-11-30 | 2026-12-06 | Task | T-14 | T-11 |  | 7 | [5 empty] | x | x |  | x | x
T-17 | Foundations | Phase 1 |  |  | Phase 1 · Foundations | Sensitive data classification (F-17) | 7 | 2026-12-07 | 2026-12-13 | Task | T-16 | T-229 |  | 7 | [5 empty] | x |  | x | x | [7 empty] | x
T-18 | Foundations | Phase 1 |  |  | Shared domain preparation | DP&E synch | 14 | 2026-11-30 | 2026-12-13 | Task | T-04 to T-08 |  |  | 14 | [5 empty] | x
T-19 | Foundations | Phase 1 |  |  | Shared domain preparation | Manual files harmonization | 14 | 2026-11-09 | 2026-11-22 | Task |  | T-10 |  | 14 | [5 empty] | x | x |  |  | x | [9 empty] | x
T-303 | Sell-In | Phase 1 | WS-1 | Migration | MX | Report assessment and preselection | 7 | 2026-11-02 | 2026-11-08 | Task |  |  |  | 7 | x
T-102 | Sell-In | Phase 1 | WS-1 | Migration | MX | Mockup | 7 | 2026-12-01 | 2026-12-07 | Task | T-303 | T-306 |  | 7 | x | [20 empty] | x
T-103 | Sell-In | Phase 1 | WS-1 | Migration | MX | Redesign | 14 | 2026-12-21 | 2027-01-03 | Task | T-102 | T-15 |  | 14 | [5 empty] | x | x |  |  |  |  | x
T-304 | Sell-In | Phase 1 | WS-1 | Migration | WACAM | Report assessment and preselection | 7 | 2026-11-09 | 2026-11-15 | Task |  | T-303 |  | 7 | x
T-106 | Sell-In | Phase 1 | WS-1 | Migration | WACAM | Mockup | 7 | 2026-12-08 | 2026-12-14 | Task | T-304 | T-102 |  | 7 | x | [21 empty] | x
T-107 | Sell-In | Phase 1 | WS-1 | Migration | WACAM | Redesign | 14 | 2026-12-28 | 2027-01-10 | Task | T-106 | T-44 |  | 14 | [5 empty] | x | x | [9 empty] | x
T-223 | Sell-In | Phase 1 | WS-1 | Migration | MX & WACAM | Manual files load | 7 | 2027-01-11 | 2027-01-17 | Task | T-103, T-107, T-04 | T-103 |  | 7 | [6 empty] | x |  |  |  |  | x
T-201 | Sell-In | Phase 1 | WS-1 | Migration | MX & WACAM | Prototype: core KPI logic | 13 | 2027-01-18 | 2027-01-30 | Task | T-223 | T-223 |  | 13 | [6 empty] | x |  |  |  |  | x
T-333 | Sell-In | Phase 1 | WS-1 | Migration | MX & WACAM | Prototype: custom features | 8 | 2027-01-31 | 2027-02-07 | Task | T-201 | T-201 |  | 8 | [6 empty] | x |  |  |  |  | x
T-109 | Sell-In | Phase 1 | WS-2 | Reverse engineer | SOCO | Analysis | 14 | 2026-11-23 | 2026-12-06 | Task | T-242 | T-209 |  | 14 |  | x |  |  |  | x | x
T-110 | Sell-In | Phase 1 | WS-2 | Reverse engineer | SOCO | Mockup | 14 | 2026-12-15 | 2026-12-28 | Task |  | T-106 |  | 14 | x | [20 empty] | x
T-242 | Sell-In | Phase 1 | WS-2 | Reverse engineer | SOCO | Capture existing code | 2 | 2026-11-02 | 2026-11-03 | Task |  |  |  | 2 | [16 empty] | x
T-111 | Sell-In | Phase 1 | WS-2 | Reverse engineer | SOCO | Redesign | 28 | 2026-12-07 | 2027-01-03 | Task | T-109 | T-348 |  | 28 | [5 empty] | x | x | [7 empty] | x
T-113 | Sell-In | Phase 1 | WS-2 | Reverse engineer | BR | Analysis | 14 | 2026-12-07 | 2026-12-20 | Task | T-243 | T-109 |  | 14 |  | x |  |  |  | x | x
T-114 | Sell-In | Phase 1 | WS-2 | Reverse engineer | BR | Mockup | 14 | 2026-12-29 | 2027-01-11 | Task |  | T-110 |  | 14 | x | [21 empty] | x
T-243 | Sell-In | Phase 1 | WS-2 | Reverse engineer | BR | Capture existing code | 3 | 2026-11-02 | 2026-11-04 | Task |  |  |  | 3 | [10 empty] | x
T-115 | Sell-In | Phase 1 | WS-2 | Reverse engineer | BR | Redesign | 28 | 2026-12-21 | 2027-01-17 | Task | T-113 | T-232 |  | 28 | [5 empty] | x | x | [6 empty] | x
T-224 | Sell-In | Phase 1 | WS-2 | Reverse engineer | SOCO & BR | Manual files load | 7 | 2027-01-18 | 2027-01-24 | Task | T-111, T-115, T-04 | T-131 |  | 7 | [6 empty] | x | [10 empty] | x
T-202 | Sell-In | Phase 1 | WS-2 | Reverse engineer | SOCO & BR | Prototype: core KPI logic | 13 | 2027-01-25 | 2027-02-06 | Task | T-224 | T-330, T-323 |  | 13 | [6 empty] | x | [7 empty] | x |  |  |  | x
T-334 | Sell-In | Phase 1 | WS-2 | Reverse engineer | SOCO & BR | Prototype: custom features | 8 | 2027-02-07 | 2027-02-14 | Task | T-202 | T-202 |  | 8 | [6 empty] | x | [7 empty] | x |  |  |  | x
T-320 | Sell-In | Security | WS-1 |  | All markets | Row level security | 7 | 2027-02-15 | 2027-02-21 | Task | T-333, T-334 | T-323, T-333 |  | 7 |  | x | [9 empty] | x
T-307 | Sell-In | Global design | WS-1 |  | All markets | Global report definition | 7 | 2027-01-26 | 2027-02-01 | Task |  | T-254 |  | 7 | x
T-290 | Sell-In | Testing | WS-1 |  | All markets | Project unit testing preparation | 14 | 2027-03-01 | 2027-03-14 | Task |  | T-320 |  | 14 |  | x
T-305 | Sell-Out | Phase 1 | WS-1 | Migration | MX | Report assessment and preselection | 7 | 2026-11-16 | 2026-11-22 | Task |  | T-304 |  | 7 | x
T-118 | Sell-Out | Phase 1 | WS-1 | Migration | MX | Mockup | 7 | 2026-12-01 | 2026-12-07 | Task | T-305 |  |  | 7 | [21 empty] | x
T-119 | Sell-Out | Phase 1 | WS-1 | Migration | MX | Redesign | 7 | 2026-12-08 | 2026-12-14 | Task | T-118 | T-13 |  | 7 | [5 empty] | x | x | [5 empty] | x
T-306 | Sell-Out | Phase 1 | WS-1 | Migration | WACAM | Report assessment and preselection | 7 | 2026-11-23 | 2026-11-29 | Task |  | T-305 |  | 7 | x
T-122 | Sell-Out | Phase 1 | WS-1 | Migration | WACAM | Mockup | 7 | 2026-12-01 | 2026-12-07 | Task | T-306 |  |  | 7 | [22 empty] | x
T-123 | Sell-Out | Phase 1 | WS-1 | Migration | WACAM | Redesign | 7 | 2026-12-08 | 2026-12-14 | Task | T-122 | T-342 |  | 7 | [5 empty] | x | x | [11 empty] | x
T-225 | Sell-Out | Phase 1 | WS-1 | Migration | MX & WACAM | Manual files load | 14 | 2026-12-15 | 2026-12-28 | Task | T-119, T-123, T-05, T-06 | T-123 |  | 14 | [6 empty] | x | [11 empty] | x
T-203 | Sell-Out | Phase 1 | WS-1 | Migration | MX & WACAM | Prototype: core KPI logic | 13 | 2026-12-15 | 2026-12-27 | Task | T-123 | T-350 |  | 13 | [6 empty] | x |  |  |  | x
T-335 | Sell-Out | Phase 1 | WS-1 | Migration | MX & WACAM | Prototype: custom features | 8 | 2027-01-07 | 2027-01-14 | Task | T-203 | T-135 |  | 8 | [6 empty] | x |  |  |  | x
T-125 | Sell-Out | Phase 1 | WS-2 | Reverse engineer | SOCO | Analysis | 14 | 2026-11-04 | 2026-11-17 | Task | T-244 |  |  | 14 |  |  | x |  |  | x | x
T-126 | Sell-Out | Phase 1 | WS-2 | Reverse engineer | SOCO | Mockup | 14 | 2026-12-01 | 2026-12-14 | Task |  |  |  | 14 | [21 empty] | x
T-244 | Sell-Out | Phase 1 | WS-2 | Reverse engineer | SOCO | Capture existing code | 2 | 2026-11-02 | 2026-11-03 | Task |  |  |  | 2 | [13 empty] | x
T-127 | Sell-Out | Phase 1 | WS-2 | Reverse engineer | SOCO | Redesign | 7 | 2026-11-18 | 2026-11-24 | Task | T-125 | T-273 |  | 7 | [5 empty] | x | x | [9 empty] | x
T-129 | Sell-Out | Phase 1 | WS-2 | Reverse engineer | BR | Analysis | 14 | 2026-11-18 | 2026-12-01 | Task | T-244 | T-125 |  | 14 |  |  | x |  |  | x | x
T-130 | Sell-Out | Phase 1 | WS-2 | Reverse engineer | BR | Mockup | 14 | 2026-12-01 | 2026-12-14 | Task |  |  |  | 14 | [22 empty] | x
T-245 | Sell-Out | Phase 1 | WS-2 | Reverse engineer | BR | Capture existing code | 3 | 2026-11-02 | 2026-11-04 | Task |  |  |  | 3 | [11 empty] | x
T-131 | Sell-Out | Phase 1 | WS-2 | Reverse engineer | BR | Redesign | 21 | 2026-12-07 | 2026-12-27 | Task | T-129 | T-211 |  | 21 | [5 empty] | x | x | [10 empty] | x
T-226 | Sell-Out | Phase 1 | WS-2 | Reverse engineer | SOCO & BR | Manual files load | 14 | 2026-12-28 | 2027-01-10 | Task | T-127, T-131, T-05, T-06 | T-322 |  | 14 | [6 empty] | x | [5 empty] | x
T-204 | Sell-Out | Phase 1 | WS-2 | Reverse engineer | SOCO & BR | Prototype: core KPI logic | 13 | 2027-01-20 | 2027-02-01 | Task | T-226, T-335 | T-143 |  | 13 | [6 empty] | x | [6 empty] | x
T-336 | Sell-Out | Phase 1 | WS-2 | Reverse engineer | SOCO & BR | Prototype: custom features | 8 | 2027-02-02 | 2027-02-09 | Task | T-204 | T-204 |  | 8 | [6 empty] | x | [6 empty] | x
T-324 | Sell-Out | Security | WS-1 |  | All markets | Row level security | 7 | 2027-02-15 | 2027-02-21 | Task | T-335, T-336 | T-193, T-46 |  | 7 |  |  | x | [10 empty] | x
T-308 | Sell-Out | Global design | WS-1 |  | All markets | Global report definition | 7 | 2027-02-02 | 2027-02-08 | Task |  | T-307 |  | 7 | x
T-294 | Sell-Out | Testing | WS-1 |  | All markets | Project unit testing preparation | 14 | 2027-03-01 | 2027-03-14 | Task |  | T-324 |  | 14 |  |  | x
T-227 | SI-SO | Phase 1 | WS-1 | Migration | MX & WACAM | Manual files load | 7 | 2027-02-08 | 2027-02-14 | Task | T-333, T-335 | T-50 |  | 7 | [15 empty] | x
T-205 | SI-SO | Phase 1 | WS-1 | Migration | MX & WACAM | Build: core KPI logic | 13 | 2027-02-16 | 2027-02-28 | Task | T-227 | T-48 |  | 13 | [6 empty] | x | [5 empty] | x
T-337 | SI-SO | Phase 1 | WS-1 | Migration | MX & WACAM | Build: custom features | 8 | 2027-03-01 | 2027-03-08 | Task | T-205 | T-205 |  | 8 | [6 empty] | x | [5 empty] | x
T-206 | SI-SO | Phase 1 | WS-2 | Discovery | BR | Analysis | 7 | 2026-11-09 | 2026-11-15 | Task |  |  |  | 7 |  | x
T-207 | SI-SO | Phase 1 | WS-2 | Discovery | BR | Mockup | 7 | 2026-12-01 | 2026-12-07 | Task |  |  |  | 7 | [21 empty] | x
T-208 | SI-SO | Phase 1 | WS-2 | Discovery | BR | Redesign | 7 | 2026-11-16 | 2026-11-22 | Task | T-206 |  |  | 7 | [7 empty] | x
T-209 | SI-SO | Phase 1 | WS-2 | Discovery | SOCO | Analysis | 7 | 2026-11-16 | 2026-11-22 | Task |  | T-206 |  | 7 |  | x
T-210 | SI-SO | Phase 1 | WS-2 | Discovery | SOCO | Mockup | 7 | 2026-12-01 | 2026-12-07 | Task |  |  |  | 7 | [22 empty] | x
T-211 | SI-SO | Phase 1 | WS-2 | Discovery | SOCO | Redesign | 7 | 2026-11-30 | 2026-12-06 | Task | T-209 | T-14 |  | 7 | [7 empty] | x | [9 empty] | x
T-228 | SI-SO | Phase 1 | WS-2 | Discovery | SOCO & BR | Manual files load | 7 | 2027-03-08 | 2027-03-14 | Task | T-211, T-208, T-334, T-336 | T-341 |  | 7 | [19 empty] | x
T-212 | SI-SO | Phase 1 | WS-2 | Discovery | SOCO & BR | Build: core KPI logic | 13 | 2027-01-15 | 2027-01-27 | Task | T-211 | T-335 |  | 13 | [7 empty] | x |  |  | x
T-338 | SI-SO | Phase 1 | WS-2 | Discovery | SOCO & BR | Build: custom features | 8 | 2027-01-28 | 2027-02-04 | Task | T-212 | T-212 |  | 8 | [7 empty] | x |  |  | x
T-321 | SI-SO | Security | WS-1 |  | All markets | Row level security | 7 | 2027-05-15 | 2027-05-21 | Task | T-337, T-338 | T-293, T-262 |  | 7 |  | x | [8 empty] | x
T-309 | SI-SO | Global design | WS-1 |  | All markets | Global report definition | 7 | 2027-02-09 | 2027-02-15 | Task |  | T-308 |  | 7 | x
T-291 | SI-SO | Testing | WS-1 |  | All markets | Project unit testing preparation | 14 | 2027-03-15 | 2027-03-28 | Task |  | T-290 |  | 14 |  | x
T-22 | Sell-Through (Snacksync) | Phase 2 | WS-3 | Discovery | LA | Analysis | 7 | 2026-11-16 | 2026-11-22 | Task | T-09 | T-145 |  | 7 |  |  |  |  | x
T-213 | Sell-Through (Snacksync) | Phase 2 | WS-3 | Discovery | LA | Mockup | 7 | 2026-11-16 | 2026-11-22 | Task | Starts with T-22 |  |  | 7
T-214 | Sell-Through (Snacksync) | Phase 2 | WS-3 | Discovery | LA | Design | 7 | 2026-11-23 | 2026-11-29 | Task | T-22 |  |  | 7 | [6 empty] | x
T-229 | Sell-Through (Snacksync) | Phase 2 | WS-3 | Discovery | LA | Manual files load | 7 | 2026-11-30 | 2026-12-06 | Task | T-214 | T-127 |  | 7 | [16 empty] | x
T-215 | Sell-Through (Snacksync) | Phase 2 | WS-3 | Discovery | LA | Build: core KPI logic | 13 | 2026-12-07 | 2026-12-19 | Task | T-229 | T-351 |  | 13 | [15 empty] | x
T-339 | Sell-Through (Snacksync) | Phase 2 | WS-3 | Discovery | LA | Build: custom features | 8 | 2026-12-20 | 2026-12-27 | Task | T-215 | T-215 |  | 8 | [15 empty] | x
T-330 | Sell-Through (Snacksync) | Security | WS-3 |  | All markets | Row level security | 7 | 2027-01-18 | 2027-01-24 | Task | T-339 | T-285, T-247 |  | 7 |  |  |  |  | x | [9 empty] | x
T-316 | Sell-Through (Snacksync) | Global design | WS-3 |  | All markets | Global report definition | 7 | 2027-02-23 | 2027-03-01 | Task |  | T-310 |  | 7 | x
T-300 | Sell-Through (Snacksync) | Testing | WS-3 |  | All markets | Project unit testing preparation | 14 | 2027-03-15 | 2027-03-28 | Task |  | T-299 |  | 14 |  |  |  |  | x
T-135 | Customer P&L | Phase 1 | WS-1 | Migration | MX | Redesign | 3 | 2027-01-04 | 2027-01-06 | Task | T-103, T-119 | T-203 |  | 3 | [6 empty] | x |  |  |  | x
T-139 | Customer P&L | Phase 1 | WS-1 | Migration | WACAM | Redesign | 4 | 2027-01-11 | 2027-01-14 | Task | T-107, T-123 | T-107 |  | 4 | [6 empty] | x | [9 empty] | x
T-230 | Customer P&L | Phase 1 | WS-1 | Migration | MX & WACAM | Manual files load | 7 | 2027-01-15 | 2027-01-21 | Task | T-135, T-139, T-07 | T-226 |  | 7 | [12 empty] | x
T-216 | Customer P&L | Phase 1 | WS-1 | Migration | MX & WACAM | Prototype: core KPI logic | 4 | 2027-03-09 | 2027-03-12 | Task | T-230 | T-337 |  | 4 | [6 empty] | x | [5 empty] | x
T-340 | Customer P&L | Phase 1 | WS-1 | Migration | MX & WACAM | Prototype: custom features | 3 | 2027-03-13 | 2027-03-15 | Task | T-216 | T-216 |  | 3 | [6 empty] | x | [5 empty] | x
T-141 | Customer P&L | Phase 1 | WS-2 | Discovery | SOCO | Analysis | 2 | 2026-11-09 | 2026-11-10 | Task |  |  |  | 2 |  |  |  |  | x
T-142 | Customer P&L | Phase 1 | WS-2 | Discovery | SOCO | Mockup | 7 | 2026-12-01 | 2026-12-07 | Task |  |  |  | 7 | [21 empty] | x
T-143 | Customer P&L | Phase 1 | WS-1 | Discovery | SOCO | Redesign | 2 | 2027-01-18 | 2027-01-19 | Task | T-141, T-111, T-127 | T-115 |  | 2 | [6 empty] | x | [6 empty] | x
T-145 | Customer P&L | Phase 1 | WS-2 | Discovery | BR | Analysis | 2 | 2026-11-11 | 2026-11-12 | Task |  | T-141 |  | 2 |  |  |  |  | x
T-146 | Customer P&L | Phase 1 | WS-2 | Discovery | BR | Mockup | 7 | 2026-12-01 | 2026-12-07 | Task |  |  |  | 7 | [22 empty] | x
T-147 | Customer P&L | Phase 1 | WS-1 | Discovery | BR | Redesign | 2 | 2027-02-05 | 2027-02-06 | Task | T-145, T-115, T-131 | T-338 |  | 2 | [6 empty] | x |  |  |  | x
T-231 | Customer P&L | Phase 1 | WS-1 | Discovery | SOCO & BR | Manual files load | 7 | 2027-02-15 | 2027-02-21 | Task | T-143, T-147, T-07 | T-45 |  | 7 | [19 empty] | x
T-217 | Customer P&L | Phase 1 | WS-1 | Discovery | SOCO & BR | Prototype: core KPI logic | 8 | 2027-02-22 | 2027-03-01 | Task | T-231 | T-231 |  | 8 | [6 empty] | x | [12 empty] | x
T-341 | Customer P&L | Phase 1 | WS-1 | Discovery | SOCO & BR | Prototype: custom features | 6 | 2027-03-02 | 2027-03-07 | Task | T-217 | T-217 |  | 6 | [6 empty] | x | [12 empty] | x
T-329 | Customer P&L | Security | WS-1 |  | All markets | Row level security | 7 | 2027-05-03 | 2027-05-09 | Task | T-340, T-341 | T-332 |  | 7 |  |  |  |  | x | [8 empty] | x
T-310 | Customer P&L | Global design | WS-1 |  | All markets | Global report definition | 7 | 2027-02-16 | 2027-02-22 | Task |  | T-309 |  | 7 | x
T-299 | Customer P&L | Testing | WS-1 |  | All markets | Project unit testing preparation | 14 | 2027-03-01 | 2027-03-14 | Task |  | T-330 |  | 14 |  |  |  |  | x
T-149 | Market Share | Phase 2 | WS-4 | Discovery | MX | Analysis | 2 | 2026-11-02 | 2026-11-03 | Task |  |  |  | 2 |  |  |  | x
T-150 | Market Share | Phase 2 | WS-4 | Discovery | MX | Mockup | 7 | 2026-11-02 | 2026-11-08 | Task | Starts with T-149 |  |  | 7
T-151 | Market Share | Phase 2 | WS-4 | Discovery | MX | Redesign | 7 | 2026-11-04 | 2026-11-10 | Task | T-149 |  |  | 7 | [7 empty] | x
T-232 | Market Share | Phase 2 | WS-4 | Discovery | MX | Manual files load | 7 | 2026-11-11 | 2026-11-17 | Task | T-151 | T-280 |  | 7 | [13 empty] | x
T-152 | Market Share | Phase 2 | WS-4 | Discovery | MX | Build: core KPI logic | 8 | 2026-11-18 | 2026-11-25 | Task | T-232 | T-238 |  | 8 | [18 empty] | x
T-342 | Market Share | Phase 2 | WS-4 | Discovery | MX | Build: custom features | 6 | 2026-11-26 | 2026-12-01 | Task | T-152 | T-152 |  | 6 | [18 empty] | x
T-153 | Market Share | Phase 2 | WS-4 | Discovery | WACAM | Analysis | 14 | 2026-11-04 | 2026-11-17 | Task |  | T-149 |  | 14 |  |  |  | x
T-154 | Market Share | Phase 2 | WS-4 | Discovery | WACAM | Mockup | 7 | 2026-11-04 | 2026-11-10 | Task | Starts with T-153 |  |  | 7
T-155 | Market Share | Phase 2 | WS-4 | Discovery | WACAM | Redesign | 7 | 2026-11-18 | 2026-11-24 | Task | T-153 |  |  | 7 | [7 empty] | x
T-157 | Market Share | Phase 2 | WS-4 | Discovery | SOCO | Analysis | 7 | 2026-11-18 | 2026-11-24 | Task |  | T-153 |  | 7 |  |  |  | x
T-158 | Market Share | Phase 2 | WS-4 | Discovery | SOCO | Mockup | 14 | 2026-11-18 | 2026-12-01 | Task | Starts with T-157 |  |  | 14
T-159 | Market Share | Phase 2 | WS-4 | Discovery | SOCO | Redesign | 7 | 2026-11-25 | 2026-12-01 | Task | T-157 |  |  | 7 | [7 empty] | x
T-161 | Market Share | Phase 2 | WS-4 | Discovery | BR | Analysis | 7 | 2026-11-25 | 2026-12-01 | Task |  | T-157 |  | 7 |  |  |  | x
T-162 | Market Share | Phase 2 | WS-4 | Discovery | BR | Mockup | 14 | 2026-11-25 | 2026-12-08 | Task | Starts with T-161 |  |  | 14
T-163 | Market Share | Phase 2 | WS-4 | Discovery | BR | Redesign | 7 | 2026-12-02 | 2026-12-08 | Task | T-161 |  |  | 7 | [7 empty] | x
T-233 | Market Share | Phase 2 | WS-4 | Discovery | WACAM, SOCO, BR | Manual files load | 7 | 2026-12-28 | 2027-01-03 | Task | T-155, T-159, T-163 | T-339 |  | 7 | [15 empty] | x
T-218 | Market Share | Phase 2 | WS-4 | Discovery | WACAM, SOCO, BR | Build: core KPI logic | 8 | 2027-02-21 | 2027-02-28 | Task | T-233 | T-49 |  | 8 | [10 empty] | x
T-343 | Market Share | Phase 2 | WS-4 | Discovery | WACAM, SOCO, BR | Build: custom features | 6 | 2027-03-01 | 2027-03-06 | Task | T-218 | T-218 |  | 6 | [10 empty] | x
T-327 | Market Share | Security | WS-4 |  | All markets | Row level security | 7 | 2027-03-30 | 2027-04-05 | Task | T-342, T-343 | T-298, T-251 |  | 7 |  |  |  | x | [8 empty] | x
T-311 | Market Share | Global design | WS-4 |  | All markets | Global report definition | 7 | 2027-03-02 | 2027-03-08 | Task |  | T-316 |  | 7 | x
T-297 | Market Share | Testing | WS-4 |  | All markets | Project unit testing preparation | 14 | 2027-03-01 | 2027-03-14 | Task |  | T-177 |  | 14 |  |  |  | x
T-165 | Perfect Store | Phase 2 | WS-5 | Discovery | MX | Analysis | 14 | 2026-12-21 | 2027-01-03 | Task | T-109, T-113, T-125, T-129 | T-161 |  | 14 |  |  |  | x
T-166 | Perfect Store | Phase 2 | WS-5 | Discovery | MX | Mockup | 14 | 2026-12-21 | 2027-01-03 | Task | Starts with T-165 |  |  | 14
T-167 | Perfect Store | Phase 2 | WS-5 | Discovery | MX | Redesign | 7 | 2027-01-04 | 2027-01-10 | Task | T-165 |  |  | 7 | [7 empty] | x
T-234 | Perfect Store | Phase 2 | WS-5 | Discovery | MX | Manual files load | 14 | 2027-01-11 | 2027-01-24 | Task | T-167 | T-35 |  | 14 | [9 empty] | x
T-168 | Perfect Store | Phase 2 | WS-5 | Discovery | MX | Build: core KPI logic | 21 | 2027-01-25 | 2027-02-14 | Task | T-234 | T-234 |  | 21 | [9 empty] | x
T-344 | Perfect Store | Phase 2 | WS-5 | Discovery | MX | Build: custom features | 14 | 2027-02-15 | 2027-02-28 | Task | T-168 | T-168 |  | 14 | [9 empty] | x
T-169 | Perfect Store | Phase 2 | WS-5 | Discovery | WACAM | Analysis | 14 | 2027-01-04 | 2027-01-17 | Task | T-109, T-113, T-125, T-129 | T-165 |  | 14 |  |  |  | x
T-170 | Perfect Store | Phase 2 | WS-5 | Discovery | WACAM | Mockup | 14 | 2027-01-04 | 2027-01-17 | Task | Starts with T-169 |  |  | 14
T-273 | Perfect Store | Phase 2 | WS-5 | Discovery | WACAM | Ingestion | 14 | 2026-11-04 | 2026-11-17 | Task | T-265 | T-242 |  | 14 | [16 empty] | x
T-171 | Perfect Store | Phase 2 | WS-5 | Discovery | WACAM | Redesign | 7 | 2027-01-18 | 2027-01-24 | Task | T-169, T-167 |  |  | 7 | [7 empty] | x
T-235 | Perfect Store | Phase 2 | WS-5 | Discovery | WACAM | Manual files load | 7 | 2027-01-25 | 2027-01-31 | Task | T-171 | T-224 |  | 7 | [17 empty] | x
T-172 | Perfect Store | Phase 2 | WS-5 | Discovery | WACAM | Build: core KPI logic | 11 | 2027-02-15 | 2027-02-25 | Task | T-235, T-273 | T-227, T-334 |  | 11 | [15 empty] | x |  |  | x
T-345 | Perfect Store | Phase 2 | WS-5 | Discovery | WACAM | Build: custom features | 7 | 2027-02-26 | 2027-03-04 | Task | T-172 | T-172 |  | 7 | [15 empty] | x |  |  | x
T-173 | Perfect Store | Phase 2 | WS-5 | Discovery | SOCO | Analysis | 14 | 2027-01-18 | 2027-01-31 | Task | T-109, T-113, T-125, T-129 | T-169 |  | 14 |  |  |  | x
T-174 | Perfect Store | Phase 2 | WS-5 | Discovery | SOCO | Mockup | 14 | 2027-01-18 | 2027-01-31 | Task | Starts with T-173 |  |  | 14
T-274 | Perfect Store | Phase 2 | WS-5 | Discovery | SOCO | Ingestion | 14 | 2026-11-02 | 2026-11-15 | Task | T-264 |  |  | 14 | [14 empty] | x
T-175 | Perfect Store | Phase 2 | WS-5 | Discovery | SOCO | Redesign | 7 | 2027-02-01 | 2027-02-07 | Task | T-173, T-171 |  |  | 7 | [7 empty] | x
T-236 | Perfect Store | Phase 2 | WS-5 | Discovery | SOCO | Manual files load | 7 | 2027-02-08 | 2027-02-14 | Task | T-175 | T-139 |  | 7 | [16 empty] | x
T-176 | Perfect Store | Phase 2 | WS-5 | Discovery | SOCO | Build: core KPI logic | 8 | 2027-02-26 | 2027-03-05 | Task | T-236, T-274 | T-324, T-248 |  | 8 | [13 empty] | x |  |  |  | x
T-346 | Perfect Store | Phase 2 | WS-5 | Discovery | SOCO | Build: custom features | 6 | 2027-03-15 | 2027-03-20 | Task | T-176 | T-219, T-352 |  | 6 | [13 empty] | x |  |  |  | x
T-177 | Perfect Store | Phase 2 | WS-5 | Discovery | BR | Analysis | 14 | 2027-02-01 | 2027-02-14 | Task | T-109, T-113, T-125, T-129 | T-173 |  | 14 |  |  |  | x
T-178 | Perfect Store | Phase 2 | WS-5 | Discovery | BR | Mockup | 14 | 2027-02-01 | 2027-02-14 | Task | Starts with T-177 |  |  | 14
T-275 | Perfect Store | Phase 2 | WS-5 | Discovery | BR | Ingestion | 14 | 2026-11-05 | 2026-11-18 | Task | T-263 | T-245 |  | 14 | [11 empty] | x
T-179 | Perfect Store | Phase 2 | WS-5 | Discovery | BR | Redesign | 7 | 2027-02-15 | 2027-02-21 | Task | T-177, T-175 |  |  | 7 | [7 empty] | x
T-237 | Perfect Store | Phase 2 | WS-5 | Discovery | BR | Manual files load | 7 | 2027-02-22 | 2027-02-28 | Task | T-179 | T-236 |  | 7 | [16 empty] | x
T-180 | Perfect Store | Phase 2 | WS-5 | Discovery | BR | Build: core KPI logic | 8 | 2027-05-15 | 2027-05-22 | Task | T-237, T-275 | T-262, T-354 |  | 8 | [11 empty] | x |  |  |  |  | x
T-347 | Perfect Store | Phase 2 | WS-5 | Discovery | BR | Build: custom features | 6 | 2027-05-23 | 2027-05-28 | Task | T-180 | T-180 |  | 6 | [11 empty] | x |  |  |  |  | x
T-328 | Perfect Store | Security | WS-5 |  | All markets | Row level security | 7 | 2027-05-29 | 2027-06-04 | Task | T-344, T-345, T-346, T-347 | T-327, T-325 |  | 7 |  |  |  | x | [8 empty] | x
T-312 | Perfect Store | Global design | WS-5 |  | All markets | Global report definition | 7 | 2027-03-09 | 2027-03-15 | Task |  | T-311 |  | 7 | x
T-298 | Perfect Store | Testing | WS-5 |  | All markets | Project unit testing preparation | 14 | 2027-03-15 | 2027-03-28 | Task |  | T-297 |  | 14 |  |  |  | x
T-182 | Right Store | Phase 2 | WS-5 | Migration | MX (DSD) | Mockup | 2 | 2026-11-02 | 2026-11-03 | Task | T-181 |  |  | 2
T-183 | Right Store | Phase 2 | WS-5 | Migration | MX (DSD) | Redesign | 7 | 2026-11-04 | 2026-11-10 | Task | T-182 |  |  | 7 | [7 empty] | x
T-238 | Right Store | Phase 2 | WS-5 | Migration | MX (DSD) | Manual files load | 7 | 2026-11-11 | 2026-11-17 | Task | T-183 |  |  | 7 | [18 empty] | x
T-184 | Right Store | Phase 2 | WS-5 | Migration | MX (DSD) | Prototype: core KPI logic | 8 | 2026-11-18 | 2026-11-25 | Task | T-238 | T-284 |  | 8 | [14 empty] | x
T-348 | Right Store | Phase 2 | WS-5 | Migration | MX (DSD) | Prototype: custom features | 6 | 2026-11-26 | 2026-12-01 | Task | T-184 | T-184 |  | 6 | [14 empty] | x
T-185 | Right Store | Phase 2 | WS-5 | Discovery | WACAM | Analysis | 14 | 2027-01-04 | 2027-01-17 | Task | Starts with T-169 | T-283 |  | 14 |  |  | x
T-186 | Right Store | Phase 2 | WS-5 | Discovery | WACAM | Mockup | 14 | 2027-01-04 | 2027-01-17 | Task | Starts with T-185 |  |  | 14
T-276 | Right Store | Phase 2 | WS-5 | Discovery | WACAM | Ingestion | 14 | 2026-11-02 | 2026-11-15 | Task | T-268 |  |  | 14 | [12 empty] | x
T-187 | Right Store | Phase 2 | WS-5 | Discovery | WACAM | Redesign | 7 | 2027-01-18 | 2027-01-24 | Task | T-185, T-183 |  |  | 7 | [7 empty] | x
T-189 | Right Store | Phase 2 | WS-5 | Discovery | SOCO | Analysis | 14 | 2027-01-18 | 2027-01-31 | Task | Starts with T-173 | T-185 |  | 14 |  |  | x
T-190 | Right Store | Phase 2 | WS-5 | Discovery | SOCO | Mockup | 14 | 2027-01-18 | 2027-01-31 | Task | Starts with T-189 |  |  | 14
T-277 | Right Store | Phase 2 | WS-5 | Discovery | SOCO | Ingestion | 14 | 2026-11-19 | 2026-12-02 | Task | T-267 | T-275 |  | 14 | [11 empty] | x
T-191 | Right Store | Phase 2 | WS-5 | Discovery | SOCO | Redesign | 7 | 2027-02-01 | 2027-02-07 | Task | T-189, T-187 |  |  | 7 | [7 empty] | x
T-193 | Right Store | Phase 2 | WS-5 | Discovery | BR | Analysis | 14 | 2027-02-01 | 2027-02-14 | Task | Starts with T-177 | T-189 |  | 14 |  |  | x
T-194 | Right Store | Phase 2 | WS-5 | Discovery | BR | Mockup | 14 | 2027-02-01 | 2027-02-14 | Task | Starts with T-193 |  |  | 14
T-278 | Right Store | Phase 2 | WS-5 | Discovery | BR | Ingestion | 14 | 2026-11-05 | 2026-11-18 | Task | T-266 | T-243 |  | 14 | [10 empty] | x
T-195 | Right Store | Phase 2 | WS-5 | Discovery | BR | Redesign | 7 | 2027-02-15 | 2027-02-21 | Task | T-193, T-191 |  |  | 7 | [7 empty] | x
T-239 | Right Store | Phase 2 | WS-5 | Discovery | WACAM, SOCO, BR | Manual files load | 7 | 2027-03-01 | 2027-03-07 | Task | T-187, T-191, T-195 | T-344 |  | 7 | [9 empty] | x
T-219 | Right Store | Phase 2 | WS-5 | Discovery | WACAM, SOCO, BR | Build: core KPI logic | 7 | 2027-03-08 | 2027-03-14 | Task | T-239, T-276, T-277, T-278 | T-239, T-176 |  | 7 | [9 empty] | x |  |  |  | x
T-349 | Right Store | Phase 2 | WS-5 | Discovery | WACAM, SOCO, BR | Build: custom features | 4 | 2027-05-15 | 2027-05-18 | Task | T-219 | T-262, T-329 |  | 4 | [9 empty] | x |  |  |  | x
T-325 | Right Store | Security | WS-5 |  | All markets | Row level security | 7 | 2027-05-19 | 2027-05-25 | Task | T-348, T-349 | T-326 |  | 7 |  |  | x | [9 empty] | x
T-313 | Right Store | Global design | WS-5 |  | All markets | Global report definition | 7 | 2027-03-16 | 2027-03-22 | Task |  | T-312 |  | 7 | x
T-295 | Right Store | Testing | WS-5 |  | All markets | Project unit testing preparation | 14 | 2027-03-15 | 2027-03-28 | Task |  | T-294 |  | 14 |  |  | x
T-24 | Shipments | Phase 2 | WS-1 | Migration | LA | Core data model | 7 | 2026-11-02 | 2026-11-08 | Task |  |  |  | 7 | [7 empty] | x
T-30 | Shipments | Phase 2 | WS-1 | Migration | LA | Redesign | 2 | 2026-11-17 | 2026-11-18 | Task | T-08 |  |  | 2 | [7 empty] | x
T-240 | Shipments | Phase 2 | WS-1 | Migration | LA | Manual files load | 7 | 2026-11-23 | 2026-11-29 | Task | T-30 | T-19 |  | 7 | [19 empty] | x
T-40 | Shipments | Phase 2 | WS-1 | Migration | LA | Build: core KPI logic | 8 | 2026-11-30 | 2026-12-07 | Task | T-240 | T-282 |  | 8 | [10 empty] | x
T-350 | Shipments | Phase 2 | WS-1 | Migration | LA | Build: custom features | 6 | 2026-12-08 | 2026-12-13 | Task | T-40 | T-40 |  | 6 | [10 empty] | x
T-322 | Shipments | Security | WS-1 |  | All markets | Row level security | 7 | 2026-12-21 | 2026-12-27 | Task | T-350 | T-113, T-119 |  | 7 |  | x | [10 empty] | x
T-314 | Shipments | Global design | WS-1 |  | All markets | Global report definition | 7 | 2027-03-23 | 2027-03-29 | Task |  | T-313 |  | 7 | x
T-292 | Shipments | Testing | WS-1 |  | All markets | Project unit testing preparation | 14 | 2027-03-29 | 2027-04-11 | Task |  | T-291 |  | 14 |  | x
T-220 | Inventory | Phase 2 | WS-1 | Migration | LA | Core data model | 7 | 2026-11-02 | 2026-11-08 | Task |  |  |  | 7 | [7 empty] | x
T-221 | Inventory | Phase 2 | WS-1 | Migration | LA | Redesign | 2 | 2026-11-09 | 2026-11-10 | Task | T-220 |  |  | 2 | [7 empty] | x
T-241 | Inventory | Phase 2 | WS-1 | Migration | LA | Manual files load | 7 | 2026-11-16 | 2026-11-22 | Task | T-221 | T-276 |  | 7 | [12 empty] | x
T-222 | Inventory | Phase 2 | WS-1 | Migration | LA | Build: core KPI logic | 8 | 2026-11-23 | 2026-11-30 | Task | T-241 | T-12 |  | 8 | [15 empty] | x
T-351 | Inventory | Phase 2 | WS-1 | Migration | LA | Build: custom features | 6 | 2026-12-01 | 2026-12-06 | Task | T-222 | T-222 |  | 6 | [15 empty] | x
T-323 | Inventory | Security | WS-1 |  | All markets | Row level security | 7 | 2026-12-29 | 2027-01-04 | Task | T-351 | T-322, T-225 |  | 7 |  | x | [16 empty] | x
T-315 | Inventory | Global design | WS-1 |  | All markets | Global report definition | 7 | 2027-03-30 | 2027-04-05 | Task |  | T-314 |  | 7 | x
T-293 | Inventory | Testing | WS-1 |  | All markets | Project unit testing preparation | 14 | 2027-04-12 | 2027-04-25 | Task |  | T-292 |  | 14 |  | x
T-280 | BR PVC | Phase 2 | WS-6 | Reverse engineer | BR | Capture existing code | 2 | 2026-11-04 | 2026-11-05 | Task |  | T-244 |  | 2 | [13 empty] | x
T-281 | BR PVC | Phase 2 | WS-6 | Reverse engineer | BR | Analysis | 7 | 2026-11-23 | 2026-11-29 | Task | T-280 | T-22 |  | 7 |  |  |  |  | x
T-61 | BR PVC | Phase 2 | WS-6 | Reverse engineer | BR | Core data model | 7 | 2026-11-30 | 2026-12-06 | Task | T-281 |  |  | 7 | [7 empty] | x
T-246 | BR PVC | Phase 2 | WS-6 | Reverse engineer | BR | Redesign | 28 | 2026-12-07 | 2027-01-03 | Task | T-61 |  |  | 28 | [7 empty] | x
T-247 | BR PVC | Phase 2 | WS-6 | Reverse engineer | BR | Manual files load | 14 | 2027-01-04 | 2027-01-17 | Task | T-246 | T-111 |  | 14 | [14 empty] | x
T-248 | BR PVC | Phase 2 | WS-6 | Reverse engineer | BR | Build: core KPI logic | 11 | 2027-02-15 | 2027-02-25 | Task | T-247 | T-334, T-288 |  | 11 | [14 empty] | x |  |  | x
T-352 | BR PVC | Phase 2 | WS-6 | Reverse engineer | BR | Build: custom features | 7 | 2027-03-06 | 2027-03-12 | Task | T-248 | T-248, T-176 |  | 7 | [14 empty] | x |  |  | x
T-331 | BR PVC | Security | WS-6 |  | All markets | Row level security | 7 | 2027-05-19 | 2027-05-25 | Task | T-352 | T-329, T-349 |  | 7 |  |  |  |  | x |  |  |  |  | x
T-317 | BR PVC | Global design | WS-6 |  | All markets | Global report definition | 7 | 2027-04-06 | 2027-04-12 | Task |  | T-315 |  | 7 | x
T-301 | BR PVC | Testing | WS-6 |  | All markets | Project unit testing preparation | 14 | 2027-03-29 | 2027-04-11 | Task |  | T-300 |  | 14 |  |  |  |  | x
T-282 | BR VR | Phase 2 | WS-6 | Reverse engineer | BR | Capture existing code | 2 | 2026-11-19 | 2026-11-20 | Task |  | T-278 |  | 2 | [10 empty] | x
T-283 | BR VR | Phase 2 | WS-6 | Reverse engineer | BR | Analysis | 7 | 2026-12-02 | 2026-12-08 | Task | T-282 | T-129 |  | 7 |  |  | x
T-249 | BR VR | Phase 2 | WS-6 | Reverse engineer | BR | Core data model | 14 | 2026-12-09 | 2026-12-22 | Task | T-283 |  |  | 14 | [7 empty] | x
T-250 | BR VR | Phase 2 | WS-6 | Reverse engineer | BR | Redesign | 28 | 2026-12-23 | 2027-01-19 | Task | T-249 |  |  | 28 | [7 empty] | x
T-251 | BR VR | Phase 2 | WS-6 | Reverse engineer | BR | Manual files load | 14 | 2027-03-16 | 2027-03-29 | Task | T-250 | T-340 |  | 14 | [12 empty] | x
T-252 | BR VR | Phase 2 | WS-6 | Reverse engineer | BR | Build: core KPI logic | 13 | 2027-03-30 | 2027-04-11 | Task | T-251 | T-228 |  | 13 | [19 empty] | x
T-353 | BR VR | Phase 2 | WS-6 | Reverse engineer | BR | Build: custom features | 8 | 2027-04-12 | 2027-04-19 | Task | T-252 | T-252 |  | 8 | [19 empty] | x
T-326 | BR VR | Security | WS-6 |  | All markets | Row level security | 7 | 2027-04-20 | 2027-04-26 | Task | T-353 | T-296, T-327 |  | 7 |  |  | x | [9 empty] | x
T-318 | BR VR | Global design | WS-6 |  | All markets | Global report definition | 7 | 2027-04-13 | 2027-04-19 | Task |  | T-317 |  | 7 | x
T-296 | BR VR | Testing | WS-6 |  | All markets | Project unit testing preparation | 14 | 2027-03-29 | 2027-04-11 | Task |  | T-295 |  | 14 |  |  | x
T-284 | BR EASTER | Phase 2 | WS-6 | Reverse engineer | BR | Capture existing code | 2 | 2026-11-16 | 2026-11-17 | Task |  | T-274 |  | 2 | [14 empty] | x
T-285 | BR EASTER | Phase 2 | WS-6 | Reverse engineer | BR | Analysis | 7 | 2026-11-30 | 2026-12-06 | Task | T-284 | T-281 |  | 7 |  |  |  |  | x
T-286 | BR EASTER | Phase 2 | WS-6 | Reverse engineer | BR | Core data model | 7 | 2026-12-07 | 2026-12-13 | Task | T-285 |  |  | 7 | [6 empty] | x
T-287 | BR EASTER | Phase 2 | WS-6 | Reverse engineer | BR | Redesign | 28 | 2026-12-14 | 2027-01-10 | Task | T-286 |  |  | 28 | [6 empty] | x
T-288 | BR EASTER | Phase 2 | WS-6 | Reverse engineer | BR | Manual files load | 14 | 2027-02-01 | 2027-02-14 | Task | T-287 | T-235 |  | 14 | [17 empty] | x
T-289 | BR EASTER | Phase 2 | WS-6 | Reverse engineer | BR | Build: core KPI logic | 7 | 2027-03-05 | 2027-03-11 | Task | T-288 | T-237, T-345 |  | 7 | [16 empty] | x |  | x
T-354 | BR EASTER | Phase 2 | WS-6 | Reverse engineer | BR | Build: custom features | 4 | 2027-03-12 | 2027-03-15 | Task | T-289 | T-289 |  | 4 | [16 empty] | x |  | x
T-332 | BR EASTER | Security | WS-6 |  | All markets | Row level security | 7 | 2027-04-26 | 2027-05-02 | Task | T-354 | T-302, T-346 |  | 7 |  |  |  |  | x | [8 empty] | x
T-319 | BR EASTER | Global design | WS-6 |  | All markets | Global report definition | 7 | 2027-04-20 | 2027-04-26 | Task |  | T-318 |  | 7 | x
T-302 | BR EASTER | Testing | WS-6 |  | All markets | Project unit testing preparation | 14 | 2027-04-12 | 2027-04-25 | Task |  | T-301 |  | 14 |  |  |  |  | x
T-35 | KPI and publish layer | Phase 1 |  |  | Phase 3 · KPI design | KPI configuration design | 14 | 2026-12-07 | 2026-12-20 | Task |  | T-16, T-240 |  | 14 | [5 empty] | x | x | x | x | x | [9 empty] | x
T-36 | KPI and publish layer | Phase 1 |  |  | Phase 3 · KPI design | Metric view design | 21 | 2026-12-21 | 2027-01-10 | Task | T-35 |  |  | 21 | [5 empty] | x |  |  | x
T-44 | KPI and publish layer | Phase 1 |  |  | Phase 3 · Publish layer | KPI mapping design (local, regional, global) | 7 | 2026-12-21 | 2026-12-27 | Task | T-35 | T-17 |  | 7 | [5 empty] | x | x |  | x | [7 empty] | x
T-45 | KPI and publish layer | Phase 1 |  |  | Phase 3 · Publish layer | Composite KPIs | 14 | 2026-12-21 | 2027-01-03 | Task | T-35 | T-35 |  | 14 | [7 empty] | x | [11 empty] | x
T-46 | KPI and publish layer | Phase 1 |  |  | Phase 3 · Publish layer | UoM conversion | 3 | 2027-02-10 | 2027-02-12 | Task | T-35 | T-336 |  | 3 | [7 empty] | x | [5 empty] | x
T-47 | KPI and publish layer | Phase 1 |  |  | Phase 3 · Publish layer | FX rate conversion | 7 | 2027-01-04 | 2027-01-10 | Task | T-45 | T-233 |  | 7 | [7 empty] | x | [7 empty] | x
T-48 | KPI and publish layer | Phase 1 |  |  | Phase 3 · Publish layer | Calendar aggregation | 3 | 2027-02-13 | 2027-02-15 | Task | T-46 | T-230 |  | 3 | [7 empty] | x |  |  |  |  | x
T-49 | KPI and publish layer | Phase 1 |  |  | Phase 3 · Publish layer | Conformed master data | 14 | 2027-02-07 | 2027-02-20 | Task | T-47 | T-147 |  | 14 | [5 empty] | x | x |  |  |  | x
T-50 | KPI and publish layer | Phase 1 |  |  | Phase 3 · Consumption | Metric views | 21 | 2027-01-11 | 2027-01-31 | Task | T-36 | T-47 |  | 21 | [5 empty] | x | [9 empty] | x
T-254 | Data governance (Ataccama) | Phase 1 |  |  | Phase 1 · Governance | Ataccama integration - KPI inventory | 14 | 2027-01-12 | 2027-01-25 | Task | T-253, T-35 | T-114 | MDLZ Data Governance | 14 | x | [6 empty] | x
T-255 | Data governance (Ataccama) | Phase 1 |  |  | Phase 1 · Governance | Ataccama integration - DQ checks | 14 | 2027-01-15 | 2027-01-28 | Task | T-253, T-12, T-335 |  | MDLZ Data Governance | 14 | [7 empty] | x
T-262 | Stabilization | Phase 1 |  |  |  | Prototype stabilization (SOW Window 1) | 60 | 2027-03-16 | 2027-05-14 | Task | All Phase 1 tasks | T-219, T-343, T-320 |  | 60 | [5 empty] | x | x | x |  | x | x | x | [8 empty] | x | x | x
T-62 | Unified LA model | Phase 1 |  |  |  | Unified LA model, sign-off | 31 | 2027-01-01 | 2027-01-31 | Task | All prototypes, T-50 |  | SteerCo, CDRB | 31
T-63 | Unified LA model | Shared |  |  |  | Full build, AWS Dev move | 59 | 2027-02-01 | 2027-03-31 | Task | T-62 |  | Data engineers | 59
T-64 | Unified LA model | Shared |  |  |  | BR, SOCO onboard by config | 31 | 2027-03-01 | 2027-03-31 | Task | SOCO and BR prototypes |  | DE, KPI stewards | 31
T-65 | Unified LA model | Shared |  |  |  | Project team test (DEV) | 30 | 2027-04-01 | 2027-04-30 | Task | T-63 |  | QA lead | 30
T-66 | Unified LA model | Shared |  |  |  | User testing (DEV) | 61 | 2027-05-01 | 2027-06-30 | Task | T-65 |  | MDLZ key users | 61
T-67 | Unified LA model | Shared |  |  |  | Integration test (QA) | 31 | 2027-07-01 | 2027-07-31 | Task | T-66 |  | QA lead | 31
T-68 | Unified LA model | Shared |  |  |  | UAT and go / no-go | 31 | 2027-08-01 | 2027-08-31 | Task | T-67 |  | MDLZ business | 31
T-69 | Unified LA model | Shared |  |  |  | Data product certification | 30 | 2027-09-01 | 2027-09-30 | Task | T-68 |  | MDLZ governance | 30
T-70 | Unified LA model | Shared |  |  |  | Go-live, 4 LA markets | 30 | 2027-09-01 | 2027-09-30 | Task | T-69 |  | Ops lead | 30
[13 empty] | Tasks per resource |  | 22 | 12 | 12 | 12 |  | 28 | 47 | 36 | 11 | 12 | 16 | 12 | 17 | 15 | 11 | 11 | 14 | 10 | 12 | 11 | 1 | 7 | 7 | 0 | 0
Legend
Analysis
Mockup
Capture existing code
Redesign / Design
Manual files load
Prototype / Build
Unified LA model
Other tasks
◆ | Milestone ◇ Deadline (needed by)

## Engagement
Parallel tasks per resource per week
Highest number of tasks the resource has on any single day of the week (tasks marked x).
|  | Oct 26 |  |  | Nov 26 |  |  |  |  | Dec 26 |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27 |  |  |  | May 27 |  |  |  |  | Jun 27 |  |  |  | Jul 27 |  |  |  | Aug 27 |  |  |  |  | Sep 27
Resource | Role | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27
BA0 | Functional lead | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BA1 | Business analyst · Sell-In, SI-SO | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BA2 | Business analyst · Sell-Out, Right Store, BR VR | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BA3 | Business analyst · Market Share, Perfect Store | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BA4 | Business analyst · Customer P&L, Sell-Through, BR PVC, BR EASTER | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DA0 | Lead architect | 0 | 0 | 0 | 3 | 3 | 4 | 5 | 5 | 9 | 7 | 6 | 5 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DA1 | Data architect · WS-1, WS-2, WS-3 | 0 | 0 | 0 | 2 | 2 | 4 | 6 | 3 | 8 | 8 | 8 | 7 | 5 | 4 | 3 | 3 | 4 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DA2 | Data architect · WS-4, WS-5, WS-6 | 0 | 0 | 0 | 5 | 4 | 4 | 2 | 3 | 5 | 4 | 3 | 3 | 3 | 4 | 6 | 3 | 3 | 1 | 3 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SA1 | Solution architect | 0 | 0 | 0 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE1 | Data engineer · Python, WS-5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE2 | Data engineer · Python, WS-5 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE3 | Data engineer · WS-1, WS-3 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE4 | Data engineer · WS-1, WS-3 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE5 | Data engineer · WS-2 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE6 | Data engineer · WS-2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE7 | Data engineer · WS-4 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE8 | Data engineer · WS-6 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE9 | Data engineer · WS-6 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE10 | Data engineer · WS-2 BR | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DE11 | Data engineer · WS-2 SOCO | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE0 | FE (role to confirm) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE1 | FE (role to confirm) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE2 | FE (role to confirm) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE3 | FE (role to confirm) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FE4 | FE (role to confirm) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0