## Sheet1
Core / Remaining per region |  |  | End Jan |  |  | End Feb
|  | Team |  | Brasil trip: 1BA_DA (prep from MDLZ) | Argentina trip: 1BA_DA (prep from MDLZ) | Brasil trip (Inventory&Shimpent): One BA for both topics Brasil trip (MarketShare) : One BA for both topics |  |  | Brasil trip: 1BA (internal onboarding) | Brasil trip: 1BA_DA (existing repo + list of questions)
Role |  | Activity | WS1 OTC+EPOS (SISO)- MX+Wacam | WS2 Brazil | WS3 SoCo | WS4 Market share + promo | WS5 Mdlz Inventory + Shipments | WS6 DSD (MX) | WS7 Perfect Store | WS8 PVC/VR/Easter | WS9 Snacksync
| (Lingaro) Tech DBX Framework | Infrastracture for the solution
BA | Discovery | Analysis from scratch |  |  |  | + |  |  | + | +
BA |  | Solution assessment and preselection |  | + | + |  |  |  |  | +
BA |  | Reverse Engineering |  | + | + |  |  |  |  | +
BA |  | (Business analysis) KPIs requirements clarification |  | + | + |  | +
BA |  | KPI's harmonization | + | + | + | + | + | + | + | +
DA_DE |  | Ingestion (Manual files) harmonization | + | + | + | + | + | + | + | +
DA |  | Solution redesign | + | + | + | + | + | + | + | +
BA |  | Global KPIs definition | + | + | + | + | + | + | + | +
DA_DE |  | Core domain build on DB using agnostic approach | + | + | + | + | + | + | + | +
DA_DE |  | Business domain build | + | + | + | + | + | + | + | +
DA_DE |  | Aggregated domain | + | + | + | + | + | + | + | +
BA |  | Use/test cases creation (for UAT) | + | + | + | + | + | + | + | +
BA_DE |  | Role level security | + | + | + | + | + | + | + | +
PBIA_PBIE |  | Consumption layer | + | + | + | + | + | + | + | +
PBIA_PBIE |  | Dashboards harmonization | + | + | + | + | + | + | + | +